## Ranking Sheet
CRFM FY20 RANKING SPREADSHEET
|  | FY20 Work Plan Budget Total $21.602M CRFM |  |  | Version: 2/19/2020 (Version 7.0)
|  | Prior FY Carry In $5.76M |  |  | Updated By: I. Chane
LCRER $1.2M
Lamprey Workplan $20.0M (additional)
Total Available in FY20 $48.566M*
Line # | Project Location | Project Title | PM | Project P2 ID | Description (FY20 Scope) | FY20 Workplan | FY20 Workplan Preliminary Cumulative | Mandatory or S&A Item Indicator (If Y Item Not Rated and Score is M) | ID Score | OR Score | WA Score | Nez Perce | Yakama Nation | Warm Springs | Umatilla | NOAA Score | FWS Score | BPA Score | CORPS Score | SCT 2020 Average Score | CURRENT REMARKS | Agency Remarks During Ranking
| Willamette | [20 empty] | District
1 | Willamette |  |  |  | Total - Willamette (NWP) | 16422 | 16422 | Y | [10 empty] | M |  | was previously $21.216M | P
Lamprey
2 | Various FCRPS |  |  |  | Total - Lamprey (NWW/NWP) | 20141 | 36563 | Y | [10 empty] | M |  | * Plan on $19M Carry In to FY21 | P/W
FCRPS
3 | ESTU | Estuary Habitat Studies | Turaski | 123452 | Woodliand Island Beneficial Uses of Dredged Material Baseline Data Collection | 275 | 36838 | N | 2 | 1 | 3 |  |  |  |  | 3 |  | 3 | 3 | 2.5 | Completion of baseline monitoring at Woodland Island | Important to complete final report on past research to inform BiOp (NOAA)
4 | ESTU | Avian Predation - Cormorant Management and Monitoring | Winters | 399072 | Implementation of DCCO EIS and DCCO Management Plan - | 200 | 37038 | Y | [11 empty] | M | Second year of Cormorant monitoring (three years post terrain mods at ESI)
11 | JDA | John Day Mitigation | Gibbons | 122434 | Analysis for JDA - TAP | 104 | 37142 | Y | [11 empty] | M | coordination with TAC and further analysis
7 | TDA | The Dalles East Fish Ladder Emergency Auxiliary Water Supply | Wright | 142630 | Planned for Closeout in FY20 | 150 | 37292 | Y | [11 empty] | M | Closeout
8 | SYS | Lower Columbia River Juvenile Survival Studies | Eppard | 156117 | Lower Columbia/estuary PIT trawl, data analysis and report; oversight | 150 | 37442 | N | 4 | 3 | 5 |  |  |  |  | 5 |  | 5 | 5 | 4.5 | PIT Trawl - budget reflects equipment needs only (trawl in FY21)
9 | SYS | Avian Island PIT Detection | Winters | 395290 | Recover PIT tags from East Sand Island DCCO and CATE colonies; analysis and reporting; oversight | 100 | 37542 | N | 4 | 3 | 4 |  |  |  |  | 4 |  | 4 | 4 | 3.8333 | Ongoing Activity
12 | BON/JDA/TDA | Reservoir Temperature Monitoring at Lower Columbia River Dams | Adams | 465995 | Planned for Closeout in FY19 | 0 | 37542 | Y | [11 empty] | M | letter report and closeout
13 | SYS | FCRPS CRFM Program Management (NWP) | Chane | 123591 | Internal and external program coordination; oversight; project and budget support | 400 | 37942 | Y | [11 empty] | M
14 | MCN | McNary Avian Deterrent Deficiency Correction and Avian Wire Design Feasibility Report | Wik | 464428 | Evaluation design and determine best approach because of impacts from high flow-debris events. | 121 | 38063 | Y | [11 empty] | M
15 | MCN | McNary Top Spill Weir (TSW) Permanence | Wik | 398029 | This is required for long term operation of the TSWs. What is in place now is a short term solution. | 145 | 38208 | N | 5 | 3 | 5 |  |  |  |  | 5 |  | 5 | 5 | 4.6667 | This construction project was funded in FY20 | Important because it is related to McNary steelhead overshoot Research (NOAA)
16 | IHR | Ice Harbor Turbine Passage Survival Program | Crum | 334588 | Contract oversight, coordination, and management. | 125 | 38333 | Y | [11 empty] | M
17 | LMN | Lower Monumental Outfall Primary Bypass Pipe Expansion Joint Deficiency Correction | Wik | 469977 | EDC, S&A and contract close out. | 92 | 38425 | Y | [11 empty] | M | Funding for corrective action
19 | LGO | Little Goose Adult Ladder Temperature Mitigation | Wik | 456609 | EDC and S&A for uninterruptable power supply. | 111 | 38536 | Y | [11 empty] | M | SA/EDC
21 | LGR | Lower Granite Spillway PIT Detection | Sands | 368299 | Construction of PIT detection system at Lower Granite spillway | 525 | 39061 | Y | [11 empty] | M | EDC and S&A / follow on work
22 | LGR | Lower Granite Spillway PIT Tag Detection - Post Construction Monitoring | Wik | 473224 | This project could be deferred to FY21 | 0 | 39061 | [12 empty] | M | Anticpate contract in FY21
23 | LGR | Lower Granite Juvenile Bypass Facility - Phase 1a (Gatewell to Separator), Phase 1b (Outfall) Close Out | Hanson | 372857 | As-builts and contract close out. Preliminary scoping for Phase 1c completion contract. | 230 | 39291 | Y | [11 empty] | M | SA/EDC and construction modifications
29 | SYS | LMO FGE SOG vs PROG (SR 10-min intake gate closure) | Wik | 464431 | Review, closeout, and equipment removal | 20 | 39311 | Y | [11 empty] | M
31 | SYS | Snake River Adult Sockeye Passage Initiatives | Wik | 461410 | Final report and project close out | 30 | 39341 | Y | [11 empty] | M | Closeout | Important work to complete eventually but rank represents relative importance if funding is limited (NOAA). Oregon Defers
32 | SYS | Inland Avian Predation | Colter | 328188 | Final report and project close out | 40 | 39381 | Y | [11 empty] | M | Close out in FY20
33 | SYS | Columbia River System Operations (CRSO) EIS | Hauenstein | 469690 | Prepare alternative impact statement | 8573 | 47954 | Y | [11 empty] | M | Increase required to balance facility account
35 | SYS | FCRPS CRFM Program Management (NWW) | Roberts | 139435 | Coordination; project and budget support | 150 | 48104 | Y | [11 empty] | M
37 | SYS | Smolt Susceptibility to Avian Predation Post-Bonneville (Placeholder) | TBD | TBD | Placeholder - Not currently in budget | 0 | 48104 | N | 3 | 3 | 3 |  |  |  |  | 3 |  | 2 | D | 2.8
39 | TDA | The Dalles Sluiceway PIT Detection Feasibility Evaluation (Placeholder) | TBD | TBD | Placeholder - Not currently in budget | 0 | 48104 | N | [11 empty] | NA
41 | SYS | Insert title (Placeholder) | Insert | Insert | Spillway and Turbine PIT Tag Detection Feasibility Study (Placeholder) | 0 | 48104 | N | 3 | 5 | 3 |  |  |  |  | 3 |  | 1 | D | 3
43 | BON | Bonneville Powerhouse 2 Fish Guidance Efficiency | Adams | 122645 | Evaluation of design and modifications to address plate issues | 300 | 48404 | Y | [11 empty] | M | Budget reflects design work and development of solicitation package
45 | SYS | Caspian Tern Management Plan (Avian Predation Monitoring) | Winters | 152054 | Planned for Closeout in FY20 | 15 | 48419 | Y | [11 empty] | M | Complete final transfer of constructed islands to state/ may need FY21 funding for transfer to federal entities
49 | BON | Bonneville PIT Detection | Ament | TBD | Assess feasibility of prototype PIT detection located at juvenile outfall piers below Bonneville Dam | 50 | 48469 | N | 3 | 5 | 4 |  |  |  |  | 4 |  | 4 | 3 | 3.8333 | Completion of EDR and DDR in FY20
50 | LGO | Little Goose Adult Ladder PIT Feasibility | TBD | TBD | Implementation of PIT detection at Little Goose ladder - based on feasibility assessment in FY18 | 0 | 48469 | N | D | D | D |  |  |  |  | 3 |  | 1 | D | 2 | Avg score does not reflect D status. Follow up to feasibility assessment -Placeholder value for install (will add budget placeholder following feasibility) | Region Defers until SRWG report Aug 23 2018.
51 | MCN | McNary Steelhead Overshoot | Wik | 479912 | Implementation of Spring study to assess overshoot of steelhead at McNary. Fall study to be awarded in FY19. | 92 | 48561 | N | 5 | 5 | 5 |  |  |  |  | 5 |  | 5 | 5 | 5 | Labor requriements to support both fall and spring in FY20. | Unclear at this point what year study will occur, but there has been an agreement among federal parties to do the study. Needs further development. (NOAA)
52 | LGR | Lower Granite and Little Goose Deep Spill vs. RSW summer subyearlings | TBD | TBD | Acoustic study to compare subyearling passage via deep spill and RSW | 0 | 48561 | N | 5 | 5 | 4 |  |  |  |  | 3 |  | 4 | D | 4.5 | Avg score does not reflect D status
53 | SYS | FCRPS Court Ordered Spill Evaluation | NA | 466539 | NO LONGER REQUIRED | 0 | 48561
54 | LGR | LGR Surface Passage Modifications | NA | 404508 | DEFERRED | 0 | 48561
55 | TDA | John Day PIT | TBD | 454951 | Closeout | 8 | 48569 | [13 empty] | O&M Manual completion for contract closeout

## Ranked Order
CRFM FY19 RANKING SPREADSHEET
| Version: 2/19/2020 (Version 7.0) | FY20 Work Plan Budget Total $21.602M CRFM
Updated By: I. Chane
#REF!
Line # | Project Location | Measure | FY20 Workplan | FY20 Workplan Preliminary Cumulative | SCT Avg Score
Willamette
1 | Willamette | Total - Willamette | 16422 | 16422 | M
2 | Various FCRPS | Lamprey (NWW/NWP) | 20141 | 36563 | M
FCRPS
3 | ESTU | Estuary Habitat Studies | 275 | 36838 | 2.5
4 | ESTU | Avian Predation - Cormorant Management and Monitoring | 200 | 37038 | M
7 | TDA | The Dalles East Fish Ladder Emergency Auxiliary Water Supply | 150 | 37188 | M
8 | SYS | Lower Columbia River Juvenile Survival Studies | 150 | 37338 | 4.5
13 | SYS | FCRPS CRFM Program Management (NWP) | 400 | 37738 | M
16 | IHR | Ice Harbor Turbine Passage Survival Program | 125 | 37863 | M
17 | LMN | Lower Monumental Outfall Primary Bypass Pipe Expansion Joint Deficiency Correction | 92 | 37955 | M
19 | LGO | Little Goose Adult Ladder Temperature Mitigation | 111 | 38066 | M
21 | LGR | Lower Granite Spillway PIT Detection | 525 | 38591 | M
22 | LGR | Lower Granite Spillway PIT Tag Detection - Post Construction Monitoring | 0 | 38591 | M
23 | LGR | Lower Granite Juvenile Bypass Facility - Phase 1a (Gatewell to Separator), Phase 1b (Outfall) Close Out | 230 | 38821 | M
29 | SYS | LMO FGE SOG vs PROG (SR 10-min intake gate closure) | 20 | 38841 | M
33 | SYS | Columbia River System Operations (CRSO) EIS | 8573 | 47414 | M
35 | SYS | FCRPS CRFM Program Management (NWW) | 150 | 47564 | M
43 | BON | Bonneville Powerhouse 2 Fish Guidance Efficiency | 300 | 47864 | M
45 | SYS | Caspian Tern Management Plan (Avian Predation Monitoring) | 15 | 47879 | M
37 | SYS | Smolt Susceptibility to Avian Predation Post-Bonneville (Placeholder) | 0 | 47879 | 2.8
49 | BON | Bonneville PIT Detection | 50 | 47929 | 3.8333
31 | SYS | Snake River Adult Sockeye Passage Initiatives | 30 | 47959 | M
32 | SYS | Inland Avian Predation | 40 | 47999 | M
9 | SYS | Avian Island PIT Detection | 100 | 48099 | 3.8333
12 | BON/JDA/TDA | Reservoir Temperature Monitoring at Lower Columbia River Dams | 0 | 48099 | M
14 | MCN | McNary Avian Deterrent Deficiency Correction and Avian Wire Design Feasibility Report | 121 | 48220 | M
39 | TDA | The Dalles Sluiceway PIT Detection Feasibility Evaluation (Placeholder) | 0 | 48220 | NA
41 | SYS | Insert title (Placeholder) | 0 | 48220 | 3
15 | MCN | McNary Top Spill Weir (TSW) Permanence | 145 | 48365 | 4.6667
11 | JDA | John Day Mitigation | 104 | 48469 | M
50 | LGO | Little Goose Adult Ladder PIT Feasibility | 0 | 48469 | 2
51 | MCN | McNary Steelhead Overshoot | 92 | 48561 | 5
52 | LGR | Lower Granite and Little Goose Deep Spill vs. RSW summer subyearlings | 0 | 48561 | 4.5