## Ranking Sheet
CRFM FY21 RANKING SPREADSHEET
|  | FY21 PBud $15.377 | Lamprey $19.937 |  | Version: 4/14/2021
|  | Willamette $3.7M | Willamette/FCRPS $22.879 |  | Updated By: I. Royer
|  | FCRPS $11.677 | $42.816 Total
Line # | Project Location | Project Title | PM | Project P2 ID | Project Description (FY21 Scope) | FY21 PBud | FY21 Mid Year Lock | FY21 Workplan Preliminary Cumulative | Mandatory or S&A Item Indicator (If Y Item Not Rated and Score is M) | ID Score | OR Score | WA Score | Nez Perce | Yakama Nation | Warm Springs | Umatilla | NOAA Score | FWS Score | BPA Score | CORPS Score | SCT 2021 Average Score | CURRENT REMARKS | Agency Remarks During Ranking
| Willamette | [21 empty] | District
1 | Willamette |  |  |  | Total - Willamette (NWP) | 3.7 | 10747 | 10747 | Y | [10 empty] | M |  |  | P
Lamprey
2 | Various FCRPS |  |  |  | Total - Lamprey (NWW/NWP)* | 0 | 1864 | 12611 | Y | [10 empty] | M |  | * Plan on $17.9M Carry In to FY21 | P/W
FCRPS
3 | ESTU | Estuary Habitat Studies | Bierman | 123452 | Post construction sampling and bathymetry at Woodland Island Section 536 restoration project. Project effectiveness monitoring | 0 | 428 | 13039 | N | 2 | 1 | 3 |  |  |  | 2 | 3 |  | 3 | 4 | 2.5714 |  | Important to complete final report on past research to inform BiOp (NOAA)
4 | ESTU | Avian Predation - Cormorant Management and Monitoring | Winters | 399072 | Implementation of DCCO EIS and DCCO Management Plan - Final Year of CRFM funding under ROD | 30 | 30 | 13069 | Y | [11 empty] | M
11 | JDA | John Day Mitigation | Chane | 122434 | Analysis for JDA - Limited Reevaluation Report / Umatilla Hatchery Trip Report | 0 | 170 | 13239 | Y | [11 empty] | M
7 | TDA | The Dalles East Fish Ladder Emergency Auxiliary Water Supply | Kovalchuk | 142630 | Engineering Design Report - assess debris management alternatives | 0 | 350 | 13589 | N | 4 | 3 | 4 |  |  |  |  | 4 |  | 4 | 4 | M
8 | SYS | Lower Columbia River Juvenile Survival Studies | Eppard | 156117 | Lower Columbia/estuary PIT trawl, data analysis and report; oversight | 1500 | 1700 | 15289 | N | 4 | 3 | 5 |  |  |  |  | 5 |  | 5 | 5 | 4.5
9 | SYS | Avian Island PIT Detection | Winters | 395290 | Recover PIT tags from East Sand Island DCCO and CATE colonies; analysis and reporting; oversight | 270 | 120 | 15409 | N | 4 | 3 | 4 |  |  |  |  | 4 |  | 4 | 4 | 3.8333
12 | BON/JDA/TDA | Reservoir Temperature Monitoring at Lower Columbia River Dams | Adams | 465995 | Planned for Closeout in FY19 | 0 | 0 | 15409 | NA | [11 empty] | M
13 | SYS | FCRPS CRFM Program Management (NWP) | Royer | 123591 | Internal and external program coordination; oversight; project and budget support | 350 | 741 | 16150 | Y | [11 empty] | M
14 | MCN | McNary Avian Deterrent Deficiency Correction and Avian Wire Design Feasibility Report | Kelly | 464428 | installation of Acoustic and Laser Deterrent system / testing in FY21 with temporary installation / requires permanent placement following testing in FY22 | 1150 | 46 | 16196 | N | 3 | 3 | 4 |  |  |  |  | 4 |  | 3 | 4 | 3.5
15 | MCN | McNary Top Spill Weir (TSW) Permanence | Bonafilia | 398029 | Final work and closeout in FY21 | 0 | 182 | 16378 | y | [11 empty] | m |  | Important because it is related to McNary steelhead overshoot Research (NOAA)
16 | IHR | Ice Harbor Turbine Passage Survival Program | Crum | 334588 | Contract modification of approximately $120k and approximately $70k in labor for field test prep. | 0 | 193 | 16571 | Y | [11 empty] | M
17 | LMN | Lower Monumental Outfall Primary Bypass Pipe Expansion Joint Deficiency Correction | Wik | 469977 | EDC, S&A and contract close out. | 0 | 0 | 16571 | NA | [11 empty] | M
19 | LGO | Little Goose Adult Ladder Temperature Mitigation | Juhnke | 456609 | Added new Work Item and $30k for Cooling Intake Sluice Gate. | 85 | 40 | 16611 | NA | [11 empty] | M
21 | LGR | Lower Granite Spillway PIT Detection | Juhnke | 368299 | Final installation of access platform and closing out in FY21 | 50 | 76 | 16687 | Y | [11 empty] | M | Follow on work?
22 | LGR | Lower Granite Spillway PIT Tag Detection - Post Construction Monitoring | Kelly | 473224 | Testing and monitoring using the newly installed pit tag detection system installed on spill bay #1 at Lower Granite | 0 | 203 | 16890 |  | 4 | 3 | 5 |  |  |  |  | 5 |  | 5 | 5 | M
23 | LGR | Lower Granite Juvenile Bypass Facility - Phase 1a (Gatewell to Separator), Phase 1b (Outfall) Close Out | Martin | 372857 & 493013 | Funding for contracts and SA/EDC in FY21 | 3500 | 2088 | 18978 | Y | [11 empty] | M
29 | SYS | LMO FGE SOG vs PROG (SR 10-min intake gate closure) | Wik | 464431 | Review, closeout, and equipment removal | 0 | 0 | 18978 | NA | [11 empty] | M
31 | SYS | Snake River Adult Sockeye Passage Initiatives | Wik | 461410 | Final report and project close out | 0 | 0 | 18978 | NA | [11 empty] | M |  | Important work to complete eventually but rank represents relative importance if funding is limited (NOAA). Oregon Defers
32 | SYS | Inland Avian Predation | Kelly | 328188 | Funding needed for Blalock Island - Reservoir operations/monitoring | 0 | 93 | 19071 | N | [11 empty] | M
33 | SYS | Columbia River System Operations (CRSO) EIS | Hauenstein | 469690 | Closeout in FY21 - possible additional need (litigation) | 1372 | 1276 | 20347 | Y | [11 empty] | M
35 | SYS | FCRPS CRFM Program Management (NWW) | Newton | 151069 | Coordination; project and budget support. Majority of PgM labor has been charged to specific NWW CRFM projects. | 150 | 17 | 20364 | Y | [11 empty] | M
37 | SYS | Smolt Susceptibility to Avian Predation Post-Bonneville (Placeholder) | TBD | TBD | Placeholder - Not currently in budget | 0 | 0 | 20364 | N | 3 | 3 | 4 |  |  |  |  | 3 |  | 2 | D | 3
39 | TDA | The Dalles Sluiceway PIT Detection Feasibility Evaluation (Placeholder) | TBD | TBD | Placeholder - Not currently in budget | 0 | 0 | 20364 | N | 2 | 5 | 5 |  |  |  |  | 5 |  | 2 | D | NA
41 | SYS | Spillway and Turbine PIT Tag Detection Feasibility Study | Insert | Insert | Spillway and Turbine PIT Tag Detection Feasibility Study (Placeholder) | 0 | 0 | 20364 | N | 4 | 5 | 5 |  |  |  |  | 4 |  | 1 | D | 3.8
43 | BON | Bonneville Powerhouse 2 Fish Guidance Efficiency | Adams | 122645 | Construction contract and A/E contract in FY 21 - two units and testing. Options for 3 additional units could be exercised pending testing. | 0 | 1860 | 22224 | Y | D | D | 3 |  | 3 |  | 3 | 5 |  | 5 | 4 | M
45 | SYS | Caspian Tern Management Plan (Avian Predation Monitoring) | Winters | 152054 | Planned for Closeout in FY21 - Real estate transfer process | 0 | 10 | 22234 | Y | [11 empty] | M
| BON | Bonneville PIT Detection | Hicks | TBD | On hold at EDR phase pending future need | 2600 | 0 | 22234 | N | 3 | 5 | 4 |  |  |  |  | 4 |  | 4 | 3 | 3.8333
50 | LGO | Little Goose Adult Ladder PIT Feasibility | TBD | TBD | Implementation of PIT detection at Little Goose ladder - based on feasibility assessment in FY18 | 0 | 0 | 22234 | N | 4 | 5 | 5 |  |  |  |  | 3 |  | 1 | 1 | 3.1667 | Keep active | Region Defers until SRWG report Aug 23 2018.
51 | MCN | McNary Steelhead Overshoot | Zelch | 479912 | Spring and fall study to assess overshoot of steelhead at McNary. Contract oversight and close out of 2nd year of study | 0 | 94 | 22328 | N | 5 | 5 | 5 |  | 5 |  |  | 5 |  | 3 | 4 | 4.5714 |  | Unclear at this point what year study will occur, but there has been an agreement among federal parties to do the study. Needs further development. (NOAA)
52 | LGR | Lower Granite and Little Goose Deep Spill vs. RSW summer subyearlings | TBD | TBD | Acoustic study to compare subyearling passage via deep spill and RSW | 0 | 0 | 22328 | N | 5 | 5 | 5 |  |  |  |  | 3 |  | 4 | D | 4.75
53 | SYS | FCRPS Court Ordered Spill Evaluation | NA | 466539 | NO LONGER REQUIRED | 0 | 0 | 22328
54 | LGR | LGR - Performance verification monitoring | NA | 334888 | Not needed | 620 | 0 | 22328
55 | TDA | John Day PIT | TBD | 454951 | Closeout | 0 | 0 | 22328

## Ranked Order
CRFM FY19 RANKING SPREADSHEET
| Version: 4/14/2021 | FY21 PBud $15.377
Updated By: I. Chane
#REF!
Line # | Project Location | Measure | FY21 PBud | FY21 Workplan Preliminary Cumulative | SCT Avg Score
Willamette
1 | Willamette | Total - Willamette | 3.7 | 3.7 | M
2 | Various FCRPS | Lamprey (NWW/NWP) | 0 | 3.7 | M
FCRPS
3 | ESTU | Estuary Habitat Studies | 0 | 3.7 | 4
4 | ESTU | Avian Predation - Cormorant Management and Monitoring | 30 | 33.7 | 0
7 | TDA | The Dalles East Fish Ladder Emergency Auxiliary Water Supply | 0 | 33.7 | 4
8 | SYS | Lower Columbia River Juvenile Survival Studies | 1500 | 1533.7 | 5
13 | SYS | FCRPS CRFM Program Management (NWP) | 350 | 1883.7 | 0
16 | IHR | Ice Harbor Turbine Passage Survival Program | 0 | 1883.7 | 0
17 | LMN | Lower Monumental Outfall Primary Bypass Pipe Expansion Joint Deficiency Correction | 0 | 1883.7 | 0
19 | LGO | Little Goose Adult Ladder Temperature Mitigation | 85 | 1968.7 | 0
21 | LGR | Lower Granite Spillway PIT Detection | 50 | 2018.7 | 0
22 | LGR | Lower Granite Spillway PIT Tag Detection - Post Construction Monitoring | 0 | 2018.7 | 5
23 | LGR | Lower Granite Juvenile Bypass Facility - Phase 1a (Gatewell to Separator), Phase 1b (Outfall) Close Out | 3500 | 5518.7 | 0
29 | SYS | LMO FGE SOG vs PROG (SR 10-min intake gate closure) | 0 | 5518.7 | 0
33 | SYS | Columbia River System Operations (CRSO) EIS | 1372 | 6890.7 | 0
35 | SYS | FCRPS CRFM Program Management (NWW) | 150 | 7040.7 | 0
43 | BON | Bonneville Powerhouse 2 Fish Guidance Efficiency | 0 | 7040.7 | 4
45 | SYS | Caspian Tern Management Plan (Avian Predation Monitoring) | 0 | 7040.7 | 0
37 | SYS | Smolt Susceptibility to Avian Predation Post-Bonneville (Placeholder) | 0 | 7040.7 | D
49 | #N/A | #N/A | #N/A | #N/A | #N/A
31 | SYS | Snake River Adult Sockeye Passage Initiatives | 0 | #N/A | 0
32 | SYS | Inland Avian Predation | 0 | #N/A | 0
9 | SYS | Avian Island PIT Detection | 270 | #N/A | 4
12 | BON/JDA/TDA | Reservoir Temperature Monitoring at Lower Columbia River Dams | 0 | #N/A | 0
14 | MCN | McNary Avian Deterrent Deficiency Correction and Avian Wire Design Feasibility Report | 1150 | #N/A | 4
39 | TDA | The Dalles Sluiceway PIT Detection Feasibility Evaluation (Placeholder) | 0 | #N/A | D
41 | SYS | Spillway and Turbine PIT Tag Detection Feasibility Study | 0 | #N/A | D
15 | MCN | McNary Top Spill Weir (TSW) Permanence | 0 | #N/A | 0
11 | JDA | John Day Mitigation | 0 | #N/A | 0
50 | LGO | Little Goose Adult Ladder PIT Feasibility | 0 | #N/A | 1
51 | MCN | McNary Steelhead Overshoot | 0 | #N/A | 4
52 | LGR | Lower Granite and Little Goose Deep Spill vs. RSW summer subyearlings | 0 | #N/A | D