## Ranking Sheet
CRFM FY19 RANKING SPREADSHEET
|  | FY2019 PBUD TOTAL $46M - $28.975M FCRPS, $17.025M Willamette, and $0 Lamprey |  |  | Version: 8/15/2018 (Version 4.0)
|  | PBud- $46M |  |  | Updated By: I. Chane
House - ?
Senate - ?
Line # | Project Location | Project Title | PM | Project P2 ID | Description (FY19 Scope) | FY19 Current Prior (May) Capability | FY19 Revised Capability (July) | FY19 Preliminary Cumulative | Mandatory or S&A Item Indicator (If Y Item Not Rated and Score is M) | ID Score | OR Score | WA Score | Nez Perce | Yakama Nation | Warm Springs | Umatilla | NOAA Score | FWS Score | BPA Score | CORPS Score | SCT 2019 Average Score | CURRENT REMARKS | Agency Remarks During Ranking
| Willamette | [22 empty] | District
1 | Willamette |  |  |  | Total - Willamette (NWP) | 19862 | 22469 | 22469 | Y | [11 empty] | M |  |  | P
Lamprey
2 | Various FCRPS |  |  |  | Total - Lamprey (NWW/NWP) | 0 | 0 | 22469 | Y | [11 empty] | M |  |  | P/W
FCRPS
3 | ESTU | Estuary Habitat Studies | Turaski | 123452 | Oversight of FY17/FY18 studies - preparation for AEMR report and synthesis in FY19 | 625 | 875 | 23344 |  | 2 | 1 | 4 |  |  |  | 3 | 5 |  | 4 | 4 |  | AEMR Study (YR 3: analysis and reporting) | Important to complete final report on past research to inform BiOp (NOAA) | P
4 | ESTU | Avian Predation - Cormorant Management and Monitoring | Winters | 399072 | Implementation of DCCO EIS and DCCO Management Plan - depredation, monitoring and terrain modifications | 750 | 750 | 24094 | [12 empty] | M | Terrain modification work delayed to FY19 - will require additional funding |  | P
11 | JDA | John Day Mitigation | Gibbons | 122434 | Analysis for JDA - TAP | 436 | 436 | 24530 | [12 empty] | M | coordination with TAC and further analysis
7 | TDA | The Dalles East Fish Ladder Emergency Auxiliary Water Supply | Wright | 142630 | SA/EDC and mod contingency; oversight | 500 | 750 | 25280 | [12 empty] | M | Closeout
8 | SYS | Lower Columbia River Juvenile Survival Studies | Eppard | 156117 | Lower Columbia/estuary PIT trawl, data analysis and report; oversight | 1600 | 1600 | 26880 |  | 4 | 3 | 3 |  |  |  | 3 | 5 |  | 5 | 5 |  | PIT Trawl |  | P
9 | SYS | Avian Island PIT Detection | Winters | 395290 | Recover PIT tags from East Sand Island DCCO and CATE colonies; analysis and reporting; oversight | 200 | 200 | 27080 |  | 4 | 3 | 4 |  |  |  | 5 | 5 |  | 4 | 4 |  |  |  | W
12 | BON/JDA/TDA | Reservoir Temperature Monitoring at Lower Columbia River Dams | Adams | 465995 | Monitoring of forebay temperatures for assessing stratification/profile (July-August). Second and final year of monitoring in 2019. | 50 | 50 | 27130 |  | 4 | 5 | 4 |  |  |  | 4 | 5 |  | 4 | 4 |  | Year 2 of monitoring and letter report
13 | SYS | FCRPS CRFM Program Management (NWP) | Chane | 123591 | Internal and external program coordination; oversight; project and budget support | 500 | 500 | 27630 | [12 empty] | M
14 | MCN | McNary Avian Water Cannon Deficiency Correction and Avian Wire Design Feasibility Report | Wik | 464428 | Evaluation design and determine best approach because of impacts from high flow-debris events. | 100 | 100 | 27730 | [12 empty] | M |  |  | P
15 | MCN | McNary Top Spill Weir (TSW) Permanence | Wik | 398029 | The contract will be awarded in early FY19. The contract is for spillway leaves to control of MCN TSWs. | 2500 | 2500 | 30230 |  | 4 | 5 | 4 |  |  |  | 4 | 5 |  | 5 | 4 |  | Added 10-18-2017 | Important because it is related to McNary steelhead overshoot Research (NOAA) | P
16 | IHR | Ice Harbor Turbine Passage Survival Program | Crum | 334588 | Characterize the pressure, sheer, and strike environment; and estimate direct injury rates and direct survival rates of juvenile salmon through the adjustable blade turbine in Unit 3 using the same methods as unit 2. | 100 | 100 | 30330 | [12 empty] | M
17 | LMN | Lower Monumental Outfall Primary Bypass Pipe Expansion Joint Deficiency Correction | Wik | 469977 | Design and construction contract award to correct joint deficiency on outfall pipe | 575 | 575 | 30905 | [12 empty] | M | Funding for corrective action |  | W
19 | LGO | Little Goose Adult Ladder Temperature Mitigation | Wik | 456609 | EDC and S&A for uninterruptable power supply. Project close out. | 100 | 100 | 31005 | [12 empty] | M |  |  | W
21 | LGR | Lower Granite Spillway PIT Detection | Heller | 368299 | EDC and S&A | 500 | 500 | 31505 | [12 empty] | M |  |  | W
22 | LGR | Lower Granite Spillway PIT Tag Detection - Post Construction Monitoring | Wik | 473224 | Monitoring award in FY18. FY19 is oversite. | 15 | 600 | 32105 | [12 empty] | M |  |  | W
23 | LGR | Lower Granite Juvenile Bypass Facility - Phase 1a (Gatewell to Separator), Phase 1b (Outfall) and Follow-On | Alturk | 372857 | EDC and S&A to complete Lower Granite Juv Bypass System. Final contract modifications for hoist system and automation. | 3000 | 3400 | 35505 | [12 empty] | M | SA/EDC and construction modifications
28 | LGR | Lower Granite Juvenile Passage Performance Verification Monitoring | Wik | 334888 | Report review and project close out | 75 | 75 | 35580 | [12 empty] | M
29 | SYS | LMO and LWG SOG vs PROG (SR 10-min intake gate closure) | Wik | 464431 | Evaluate Fish Guidance Efficiency (FGE) at Lower Monumental Dam with intake head gates in a raised versus lowered position. FY19 = Equipment deployment, field study, operating project assists with gate moves, etc., preliminary results | 100 | 100 | 35680 | [12 empty] | M |  |  | W
30 | SYS | Snake River Intake Gate Closure | Heller | 149683 | project close out | 10 | 10 | 35690 | [12 empty] | M | Mandatory for safety. |  | W
31 | SYS | Snake River Adult Sockeye Passage Initiatives | Wik | 461410 | FY19 activities will include wrapping up the trap and haul assessment and temperature reduction possibilities at Lower Monumental, Ice Harbor and McNary Dams. | 275 | 275 | 35965 |  | 4 |  | 4 |  |  |  | 2 | 3 |  | 4 | 4 |  | Temperature modeling / Scope refinement | Important work to complete eventually but rank represents relative importance if funding is limited (NOAA). Oregon Defers
32 | SYS | Inland Avian Predation | Colter | 328188 | Final report and project close out | 150 | 150 | 36115 | [12 empty] | M | Final year FY19
33 | SYS | Columbia River System Operations (CRSO) EIS | Gibbons | 469690 | Prepare alternative impact statement | 7800 | 7800 | 43915 | [12 empty] | M
34 | SYS | Snake River Fall Chinook System Survival Study | Wik | 149671 | In-house labor for report reviews, regional coordination and project closeout activities | 35 | 35 | 43950 | [12 empty] | M | Study completion / report
35 | SYS | FCRPS CRFM Program Management (NWW) | McGill | 139435 | Coordination; project and budget support | 400 | 400 | 44350 | [12 empty] | M |  |  | P
37 | SYS | Smolt Susceptibility to Avian Predation Post-Bonneville (Placeholder) | TBD | TBD | Placeholder - Not currently in budget | 0 | 0 | 44350 |  | 5 | 3 | 4 |  |  |  | 4 | 3 |  | 2 | 1
39 | TDA | The Dalles Sluiceway PIT Detection Feasibility Evaluation (Placeholder) | TBD | TBD | Placeholder - Not currently in budget | 0 | 0 | 44350 |  | 4 | 5 | 4 |  |  |  | 3 | 4 |  | 1 | 1
41 | SYS | Insert title (Placeholder) | Insert | Insert | Spillway and Turbine PIT Tag Detection Feasibility Study (Placeholder) | 0 | 0 | 44350 |  | 5 | 5 | 4 |  |  |  | 3 | 3 |  | 1 | 1
42 | SYS | FCRPS Spill to Gas Cap - Hydro surveys / physical model / Adult and Juvenile Studies | Ament | 466539 | Juvenile and adult passage and survival studies; oversight and coordination | 11300 | 700 | 45050 | [12 empty] | M
43 | BON | Bonneville Powerhouse 2 Fish Guidance Efficiency | Medina | 122645 | Evaluation of design and modifications to address plate issues | 350 | 500 | 45550 | [12 empty] | M | Budget does not reflect design and installation of fix (would require additional funding)
44 | BON | Bonneville Powerhouse 2 Floating Orifice Gates/Bulkheads | Ball | 466128 | Installation of bulkheads on the Bonn Floating Orifice Gates | 935 | 250 | 45800 | [12 empty] | M | SA/EDC pending FY18 ability to exercise contract options for all bulkheads
45 | SYS | Caspian Tern Management Plan (Avian Predation Monitoring) | Winters | 152054 | Regular monitoring, hazing and dissuasion on East Sand Island and Corps constructed islands; oversight and closeout | 0 | 0 | 45800 | [12 empty] | M | Final year FY18
49 | BON | Bonneville PIT Detection | TBD | TBD | Assess feasibility of prototype PIT detection located at juvenile outfall piers below Bonneville Dam | 160 | 200 | 46000 |  | 4 | 5 | 4 |  |  |  | 4 | 5 |  | 5 | 5 |  | Evaluation of placement and prototype development/intsallation in FY19
50 | LGO | Little Goose Adult Ladder PIT Feasibility | TBD | TBD | Implementation of PIT detection at Little Goose ladder - based on feasibility assessment in FY18 | 450 | 0 | 46000 | [13 empty] | Follow up to feasibility assessment -Placeholder value for install (will add budget placeholder following feasibility) | Region Defers until SRWG report Aug 23 2018.
51 | MCN | McNary Steelhead Overshoot | TBD | TBD | Implementation of study to assess overshoot of steelhead at McNary (post PIT FY18 assessment) | 0 | 0 | 46000 |  | 5 | 5 | 4 |  |  |  | 4 | 5 |  | 2 | 4 |  | Requires refinement of study and BPA coordination | Unclear at this point what year study will occur, but there has been an agreement amoung federal parties to do the study. Needs further development. (NOAA)

## Ranked Order
CRFM FY19 RANKING SPREADSHEET
| Version: 8/15/2018 (Version 4.0) | FY2019 PBUD TOTAL $46M - $28.975M FCRPS, $17.025M Willamette, and $0 Lamprey
Updated By: I. Chane
PBud- $46M
Line # | Project Location | Measure | FY19 Current Prior (May) Capability | FY19 Preliminary Cumulative | SCT 2019 Average Score
Willamette
1 | Willamette | Total - Willamette | 22469 | 22469 | M
2 | Various FCRPS | Lamprey (NWW/NWP) | 0 | 22469 | M
FCRPS
3 | ESTU | Estuary Habitat Studies | 875 | 23344 | 0
4 | ESTU | Avian Predation - Cormorant Management and Monitoring | 750 | 24094 | M
7 | TDA | The Dalles East Fish Ladder Emergency Auxiliary Water Supply | 750 | 24844 | M
8 | SYS | Lower Columbia River Juvenile Survival Studies | 1600 | 26444 | 0
13 | SYS | FCRPS CRFM Program Management (NWP) | 500 | 26944 | M
16 | IHR | Ice Harbor Turbine Passage Survival Program | 100 | 27044 | M
17 | LMN | Lower Monumental Outfall Primary Bypass Pipe Expansion Joint Deficiency Correction | 575 | 27619 | M
19 | LGO | Little Goose Adult Ladder Temperature Mitigation | 100 | 27719 | M
21 | LGR | Lower Granite Spillway PIT Detection | 500 | 28219 | M
22 | LGR | Lower Granite Spillway PIT Tag Detection - Post Construction Monitoring | 600 | 28819 | M
23 | LGR | Lower Granite Juvenile Bypass Facility - Phase 1a (Gatewell to Separator), Phase 1b (Outfall) and Follow-On | 3400 | 32219 | M
28 | LGR | Lower Granite Juvenile Passage Performance Verification Monitoring | 75 | 32294 | M
29 | SYS | LMO and LWG SOG vs PROG (SR 10-min intake gate closure) | 100 | 32394 | M
30 | SYS | Snake River Intake Gate Closure | 10 | 32404 | M
33 | SYS | Columbia River System Operations (CRSO) EIS | 7800 | 40204 | M
34 | SYS | Snake River Fall Chinook System Survival Study | 35 | 40239 | M
35 | SYS | FCRPS CRFM Program Management (NWW) | 400 | 40639 | M
43 | BON | Bonneville Powerhouse 2 Fish Guidance Efficiency | 500 | 41139 | M
44 | BON | Bonneville Powerhouse 2 Floating Orifice Gates/Bulkheads | 250 | 41389 | M
45 | SYS | Caspian Tern Management Plan (Avian Predation Monitoring) | 0 | 41389 | M
37 | SYS | Smolt Susceptibility to Avian Predation Post-Bonneville (Placeholder) | 0 | 41389 | 0
42 | SYS | FCRPS Spill to Gas Cap - Hydro surveys / physical model / Adult and Juvenile Studies | 700 | 42089 | M
49 | BON | Bonneville PIT Detection | 200 | 42289 | 0
31 | SYS | Snake River Adult Sockeye Passage Initiatives | 275 | 42564 | 0
32 | SYS | Inland Avian Predation | 150 | 42714 | M
9 | SYS | Avian Island PIT Detection | 200 | 42914 | 0
12 | BON/JDA/TDA | Reservoir Temperature Monitoring at Lower Columbia River Dams | 50 | 42964 | 0
14 | MCN | McNary Avian Water Cannon Deficiency Correction and Avian Wire Design Feasibility Report | 100 | 43064 | M
39 | TDA | The Dalles Sluiceway PIT Detection Feasibility Evaluation (Placeholder) | 0 | 43064 | 0
41 | SYS | Insert title (Placeholder) | 0 | 43064 | 0
15 | MCN | McNary Top Spill Weir (TSW) Permanence | 2500 | 45564 | 0
11 | JDA | John Day Mitigation | 436 | 46000 | M
50 | LGO | Little Goose Adult Ladder PIT Feasibility | 0 | 46000 | 0
51 | MCN | McNary Steelhead Overshoot | 0 | 46000 | 0