Fish Facility DDR Content at 30%, 60%, and 90% Milestones

30% DDR:

- Identify design criteria, references, loads, and assumptions

- Biological:

  - Identify species of concern, fish size and numbers, and run-timing

  - Identify any other species that could be indirectly affected

  - Identify sorting, anesthetic, and sampling criteria

  - Identify water quality criteria

  - Identify criteria (e.g. fish collection efficiency, survival and injury) for each feature (i.e. fish ladder, holding pools, etc)

  - Identify handling/transport criteria

  - Identify release site(s)

  - Identify post-construction monitoring and evaluation and any RME equipment (e.g. PIT antennas) that could be installed as part of the construction

- Geotechnical:

- Site geology

- Groundwater conditions

- Remediation of subsurface contamination

- Results of subsurface explorations

- Hydrologic and Hydraulic:

  - Identify pertinent data including constraints and general hydraulic characteristics

  - Perform hydrologic analysis, if not done during EDR, and develop flow exceedance curves

  - Establish the design high flow and low project outflows for fish collection operations

  - Identify tailwater elevations

  - Identify pertinent reservoir elevations

  - Identify general hydraulic features

  - Develop numerical model(s) of the system to inform the design

  - Identify and initiate development of physical modeling (if not done during EDR), if determined necessary

  - Identify flow requirements and preliminarily size each feature

  - Identify potential impacts to operations, if applicable

- Structural:

- Develop structural load cases

- Identify structural materials

- Perform preliminary structural analysis to determine size of each feature or primary member

- Preliminary 3D models and isometric views

- Mechanical:

- Identify mechanical systems, components, and operations

- Identify list of mechanical drawings

- Electrical:

- Power sources identified

- Overall plant control system identified

- Prepare electrical SKM model

- Prepare one line diagrams and block diagrams

60% DDR:

- Update DDR text

- Identify Appendices

- Biological

  - Update with any new information/address placeholders

- Geotechnical:

  - Identify borrow and disposal sites

  - Identify design parameters (earth pressures, seismic parameters, soil/rock parameters)

  - Excavation design

  - Cofferdam/temporary retaining structures design

- Hydrologic and Hydraulic:

  - Continue sizing and configuration of the geometry of each component and checking for biological/hydraulic criteria compliance (iterative process)

  - Perform numerical model(s) of the system to inform the design

  - Complete development and perform physical modeling, if determined necessary

  - Finalize component sizing

  - Determine hydraulic loads as needed for structural/mechanical design

  - Submit design calculations

- Structural:

- Finalize stability analysis or primary structures/components

- Perform preliminary strength design

- 3D models of structures, isometrics, concrete outlines, section views of primary structures

  - Continue sizing and configuration of each component and checking for biological/hydraulic criteria compliance (iterative process)

  - Identify structures that could be added later included in the design to address major risks identified for meeting the biological criteria.

- Mechanical:

- Develop mechanical systems, components, and operations plans

- Preliminary list of electrical loads

- Identify mechanical equipment

- Preliminary drawings showing mechanical equipment layout

- Electrical:

- Control systems interface with existing project systems identified

- Update load studies and vault studies

- Update electrical SKM model

- Conductor sizing calculations for major feeders and branch circuits

- Voltage drop and grounding calculations completed

- One line drawings and block diagrams for control and communications completed

- Construction/Civil/Real Estate/Cost:

- Identify staging areas and real estate needs.

- Preliminary demo/construction sequencing

- Draft construction schedule

- Prepare cost estimate from draft list of DDR quantities

90% DDR:

- Finalize DDR text

- Finalize Appendices (explorations, calculations, site surveys, etc)

- Biological:

  - Develop fish salvage/rescue plan for use during construction

  - Develop fish salvage/rescue plan for use when the facility is operational

- Geotechnical:

  - Ground improvement design

  - Embankment design

  - Foundation design (for each structure)

  - Geotechnical retaining structures design

  - Corrosion mitigation design

  - Instrumentation requirements

  - Drawings – Embankment and foundations

- Hydrologic and Hydraulic:

  - Continue coordination of biological/hydraulic criteria compliance (iterative process)

  - Develop operational schemes/input to operations plans

  - Develop emergency operations procedures/input to operations plans.

  - Develop normal startup and shutdown procedures/input to operations plans.

- Structural:

- Finalize structural analysis of all structural features

  - Continue sizing and configuration of each component and checking for biological/hydraulic criteria compliance (iterative process)

  - Identify structures that could be added later included in the design to address major risks identified for meeting the biological criteria.

- 3D models of structures, isometrics, construction/demo sequence drawings, plan views, section views, typical structural details

- Mechanical:

- Finalize mechanical systems, components, and operations plans

- Finalize list of electrical loads

- Finalize DDR drawings showing mechanical equipment layout and details

- Electrical:

- Finalize load and fault studies

- Perform load analysis

- Perform short circuit analysis

- Equipment sizing calculations

- Lighting calculations

- Perform voltage drop/feeder size calculations

- Grounding calculations

- Electrical plans, demo drawings, one lines, panel schedules, block diagrams from control and communications

- Construction/Civil/Real Estate/Cost:

- Finalize staging and real estate needs

- Finalize demo/construction sequencing

- Finalize DDR construction schedule

- Prepare cost estimate from final list of DDR quantities