## Slide 1: Cougar Downstream passage 60% DDR Progress update
Chris Budai, PM
Jeremy Britton, TL
Scott Fielding, PM-E
Logan Negherbon, EC-HD
Ryan Souders, EC-DM
7 November 2017

## Slide 2: Meeting Purpose
Discuss the 60% Design Documentation Report (DDR) with WFFDWG
  Risk Factors Driving Design
  How Design Address Risk Factors
  Focus Areas Moving Forward
Far field
Near field

## Slide 3: Schedule
60% DDR
  WFFDWG review – November 1 – December 11, 2017
Overall Project Schedule
  DDR Complete – April 2018
  Plans & Specifications Complete – September 2019
  Award – Construction – Third Quarter 2020
  Construction Complete – 2022

## Slide 4: Risk Factors Driving Design
Location
  Cul-de-sac
  Entrance near Water Temperature Control Tower (WTCT)
Pool Fluctuation
  Fish collection from 1532 feet to 1690 feet
Flow
  Design flow
  Competing flow
Entrance
  Shape and configuration
  Fish collection 20 to 30 feet below water surface

## Slide 5: Location within Reservoir

## Slide 6: Location in the Cul-de-sac
WTCT
CRANE PAD
PARKING
LOT
PARKING
LOT
COUGAR
RESERVOIR
RUSH
CREEK
EL.1699
EL.1541
EL. 1470

## Slide 7: Location – Near Water Temperature Control tower
WTCT
MOORING
TOWER
FSS
AMPHIBIOUS
VEHICLE
MOORING
TOWER
FSS
WTCT
AMPHIBIOUS
VEHICLE

## Slide 8: Pool Fluctuations

## Slide 9: Design Flow: 300 – 1,000 cfs
400 600

## Slide 10: flow
FSS design flow is 300 cfs to 1,000 cfs
This covers the majority of outflows
Two months when flows often above 1,000 cfs
AND fish are passing:
Fry in May (pool above 1571)
Yearlings in January (pool below 1571)
When pool is above 1571, excess flow passes over WTCT weirs – fish don’t like to pass trash racks in front of weirs
When pool is below 1571, excess flow passes RO bypass gate

## Slide 11: Entrance shape & Configuration
16 FT
25 FT
PRIMARY SCREENS
310-420 CFS
SECONDARY
SCREENS
145-195 CFS
ENTRANCE
RAMP
≈ 2/3 of the flow
≈ 1/3 of the flow

## Slide 12: Water Movement Through System
PRIMARY DEWATERING
SECONDARY DEWATERING
PRIMARY DEWATERING
SECONDARY DEWATERING

## Slide 13: Fish Movement Through System
AV W/ TRANSPORT TANK
CAPTURE VELOCITY
~7.25 FT/S TAKES PLACE
WITHIN THE SECONDARY SCREENS.

## Slide 14: Focus areas moving forward
  FSS Entrance:
  Hydraulic modeling (CFD and physical)
Potential adaptive management measures:
  Guidance structures (e.g. nets)
  Reservoir operations
  Modifiable FSS entrance
Other:
  Debris management
  Rock excavation
  Defining O&M needs
  WTCT weir leakage

## Slide 15: Extra slides

## Slide 16
Daily Exceedance Outflow (cfs)
Percent of Fish Available for Passage with FSS