## Willamette Interim Measures
Willamette Interim Measures - DRAFT
Updated 3/30/2021
Measure # | Measure Type | Short Title | Subbasin | Projected Implementation Date | Duration | Status | Notes
1 | Habitat | Work with WATER Habitat Technical Team to identify a third-party sponsor to propose project(s) for large wood placement below dams | Willamette Basin
2 | Habitat | Work with WATER Habitat Technical Team to identify a third-party sponsor to propose project(s) to place sediment below dams | Willamette Basin
3 | Hatchery | Assessment of the potential benefits of reducing or ending stocking non-native hatchery trout into Willamette reservoirs associated with the Corps' Willamette Trout Hatchery Mitigation Program | Willamette Basin | By July 2021
4 | US Passage (Genetic Pedigree) | Genetic pedigree analysis of adult spring Chinook returns to Minto Trap using data collected through 2019 | North Santiam |  | Ongoing | Ongoing | ongoing
5 | Operation / DS Fish Passage | Detroit fall/winter downstream fish passage operation | North Santiam | Fall/Winter 2020 | Annually, during drawdown and throughout winter (Nov-Feb) | Implemented beginning in Nov 2020
6 | Operation / Water Quality | Big Cliff TDG operation | North Santiam | Fall/Winter 2020 | Ongoing anytime flows exceed PH | Implemented beginning in fall 2020; future implementation dependent on availability of spillway gates
7 | Operation / DS Fish Passage / Temperature | Detriot spring/summer/fall temperature and downstream fish passage operation | North Santiam | June 2021 | Annually, approximately June-Nov | Anticipated to begin in Apr 2021
9 | Operation / DS Fish Passage | Foster fall/winter and spring downstream fish passage operation | South Santiam | Fall/Winter 2020 + Spring 2021 | Annually, approximately Oct 16-Dec 15 and Mar 1-June 15 | Implemented beginning in Oct 2020; currently ongoing | ongoing
10 | Operation / US Fish Passage | Foster summer temperature and TDG operation. | South Santiam | Summer (July) 2020 | Annually, 1-2 months (approximately July-Aug) | Implemented beginning in summer 2020
11 | Hatchery | South Santiam River outplant site evaluation | South Santiam
12 | Operation / Flows | Green Peter fall flow augmentation | South Santiam | Fall 2020 | Annually, in fall in coordination with BPA | Implemented beginning in fall 2020
13 | Hatchery | Assessment of the potential benefits of reducing hatchery spring Chinook releases in the South Santiam River associated with the Corps' Willamette Spring Chinook Hatchery Mitigation Program | South Santiam | By July 2021
14 | US Passage (Genetic Pedigree) | Genetic pedigree analysis of adult spring Chinook returns to Cougar Trap using data collected through 2019 | McKenzie |  | Ongoing | Ongoing | ongoing
15 | Operation / DS Fish Passage | Cougar temperature tower split gate operation to minimize fish passage rates through the regulating outlet | McKenzie | Summer 2020 | Annually, summer to drawdown | Modified operation implemented beginning in summer 2020 | With agreement by NMFS and BPA, operation was revised in summer 2020 to continue with surface spill instead of implementing split gate operation. Since fish are lower in water column during summer, split gate would have passed fish that the agencies did not want to pass.
16 | Operation / DS Fish Passage | Cougar limited refill for downstream fish passage operation | McKenzie |  | Annually, approximately Jan-Sep |  | Likely requires additional NEPA analysis prior to a decision on implementation.
17 | Operation / DS Fish Passage | Model Cougar delayed refill for downstream fish passage operation; determine whether to implement instead of Measure 16 | McKenzie |  | Annually, approximately Feb-June |  | Likely requires additional NEPA analysis prior to a decision on implementation.
18 | US Passage | Dexter Trap best management practices | MF Willamette
19 | Hatchery | Assessment of the potential benefits of reducing hatchery spring Chinook releases in the Middle Fork Willamette River associated with the Corps' Willamette Spring Chinook Hatchery Mitigation Program | MF Willamette | By July 2021
20 | Operation / DS Fish Passage | Hills Creek winter/spring downstream passage operation | MF Willamette | Winter 2021 | Annually, approximately Dec-Mar | Anticipated to begin in Dec 2021
21 | Operation / DS Fish Passage | Lookout Point spring/summer downstream fish passage operation | MF Willamette | Spring 2021 | Annually, approximately Apr-Sep | Anticipated to begin in Apr 2021
22 | DS Fish Passage | Fall Creek trap and haul downstream fish passage operation | Fall Creek | Winter 2021 | Annually, approximately Jan-May
23 | Operation / DS Fish Passage | Fall Creek spring downstream fish passage operation | Fall Creek |  | Annually, approximately May-July |  | Likely requires additional NEPA analysis prior to a decision on implementation.